## All Tasks
Task Type | BBB SKU# | RequestID | Status | Responsible | Assigned To | Requested Date | Assignment Date | Due Date | Completion Date | New Due Date
PPAP Review | MMM2017 | 658 | In progress | Felix Kaplun | John Amyot | 2017-04-21 | 2017-05-16 | 2017-05-17
Feasibility - Product Engineering | 2017-02-14 | 703 | In progress | Felix Kaplun | John Amyot | 2017-05-12 | 2017-05-12 | 2017-05-12
Reverse Enginnering Start | YYYYY777 | 725 | In progress | Felix Kaplun | Andrey Timofeev | 2017-06-09 | 2017-06-09 | 2017-06-09
Feasibility - Product Engineering | TEST_BBB_SKU_bom_2017-05-05 | 727 | In progress | Felix Kaplun | John Amyot | 2017-05-15 | 2017-05-15 | 2017-05-15
Process Design | 2017-05-18 | 709 | In progress | Felix Kaplun | John Amyot | 2017-05-19 | 2017-05-22 | 2017-05-22
New Engineering Req |  | 704 | In progress | John Amyot | John Amyot | 2017-04-14 | 2017-04-14 | 2017-05-09
New Engineering Req |  | 720 | In progress | John Amyot | John Amyot |  | 2017-05-11 | 2017-05-11
New Engineering Req |  | 722 | In progress | John Amyot | John Amyot | 2017-05-11 | 2017-05-11 | 2017-05-11
New Engineering Req |  | 723 | In progress | John Amyot | John Amyot | 2017-05-11 | 2017-05-11 | 2017-05-11
PPAP Test Plan |  | 733 | In progress | John Amyot | John Amyot | 2017-05-17 |  | 2017-05-17
PPAP Test Plan |  | 743 | In progress | John Amyot | John Amyot | 2017-05-22 | 2017-05-22 | 2017-05-24
New Component Request |  | 747 | In progress | Andrey Timofeev | Andrey Timofeev
New Component Request |  | 750 | In progress | Andrey Timofeev | Andrey Timofeev
Due diligence |  | 751 | In progress | Felix Kaplun | John Amyot | 2017-05-26 | 2017-05-29 | 2017-05-31
New Product Line |  | 758 | In progress | John Amyot | Andrey Timofeev | 2017-05-26 | 2017-05-26 | 2017-05-26
New Component Request |  | 773 | In progress | John Amyot | John Amyot
New Component Request |  | 791 | In progress | John Amyot | John Amyot |  |  | 2017-06-13
Due diligence |  | 794 | In progress | Felix Kaplun | John Amyot | 2017-06-14 | 2017-06-14 | 2017-06-14
Due diligence |  | 795 | In progress | Felix Kaplun | John Amyot | 2017-06-14 | 2017-06-14 | 2017-06-14